## January Report
Date | Deatils | Status
2024-01-08 | Software development (Criterion 2) | Completed
2024-01-09 | Software development (Criterion 3) | Completed
2024-01-10 | Software development (Criterion 4) | Completed
| Webinar Details | Completed
2024-01-11 | Software development (Criterion 5) | Pending
2024-01-12 | Software development (Criterion 5) | Completed
| Software development (Criterion 6) | Completed
2024-01-13 | Software development (Criterion 7) | Completed
2024-01-14 | Sunday Holiday
2024-01-15 | Sankranthi Holiday
2024-01-16 | Explaining Intern's their task for next 15 Days in detail [Archana (NAAC),Ritika(NBA)] | Completed
| Working on Admin Setting Calender Year for user | Pending
2024-01-17 | Working on Admin Setting Calender Year for user | Completed
2024-01-18 | Designing Admin Panel and Dashboard
| Explained Ritika Creation of Flask Application of NBA | Completed
2024-01-19 | Implementation of Admin Set Calender to User | Completed
2024-01-20 | Made some changes in the Flask Apllication(Back-End) Criterion 1,2,3 and Dashboard | Completed
2024-01-21 | Sunday Holiday
2024-01-22 | Made some changes in the Flask Apllication(Back-End) Criterion 4,5,6,7 | Completed
| Redesigning the HTML Page's according to Mobile View | Pending
2024-01-23 | Redesigning the HTML Page's according to Mobile View | Pending
2024-01-24 | Redesigning the HTML Page's according to Mobile View | Completed
2024-01-25 | Research on My-SQL Database | Completed
2024-01-26 | Republic Day
2024-01-27 | Studying SRS | Pending
2024-01-28 | Sunday Holiday
2024-01-29 | Internship Completion letter and Internship Cretificate Format Design | Completed
| Backend Calculation (Criterion 1.3) | Completed
2024-01-30 | Set Calendar Front End Design | Pending
2024-01-31 | Set Calendar Front End Design | Completed

## February Report
Date | Deatils | Status
2024-02-01 | Set Calendar Back End extraction | Completed
2024-02-02 | Set Target Designing | Pending
2024-02-03 | Set Target Designing | Completed
2024-02-04 | Sunday
2024-02-05 | Update of project so far complted | Completed
| Discussion regarding Requirement of project | Completed
| Git Repo Access to Raghav | Completed
2024-02-06 | Research on sutiable DB connection to project | Pending
| Asigned University Data Sort to Ritika[Maharastra] | Completed
2024-02-07 | Research on sutiable DB connection to project | Pending
| Asigned University Data Sort to Ritika[Rajasthan] | Completed
2024-02-08 | Research on sutiable DB connection to project | Pending
2024-02-09 | Research on sutiable DB connection to project | Completed
2024-02-10 | Implementation of Database | Pending
2024-02-11 | Sunday
2024-02-12 | Implementation of Database | Completed
| Linking set calender with Database | Completed
2024-02-13 | Login Validation Admin | Completed
2024-02-14 | Database connection [Set Target] | Completed
2024-02-15 | Add Responsibility Page design and deployment | Completed
2024-02-16 | Responsibility user login page and validation | Pending
2024-02-17 | Responsibility user login page and validation | Completed
2024-02-18 | Sunday
2024-02-19 | Made changes to add responsibility page made corrections to avoid duplicate entries | Completed
| User Login and and validation | Completed
| Targets displayed as notifications to user | Completed
| Changes in set target page | Completed
2024-02-20 | Leave
2024-02-21 | Leave
2024-02-22 | Change Password Implementaion Admin end | Pending
2024-02-23 | Change Password Implementaion Admin end | Completed
2024-02-24 | Design of update target page | Pending
2024-02-25 | Sunday
2024-02-26 | Design of update target page | Completed
2024-02-27 | Change Password Impementation User End | Completed
2024-02-28 | Update Target BackEnd Implementation | Pending
2024-02-29 | Update Target BackEnd Implementation | Pending

## March Report
Date | Deatils | Status
2024-03-01 | Update Target BackEnd Implementation | Completed
2024-03-02 | Changes in Change Password | Pending
2024-03-03 | Sunday
2024-03-04 | Redesign of login page | Completed
| Changes in Set Target Front End | Pending
2024-03-05 | Changes in Set Target Front End | Pending
2024-03-06 | Changes in Set Target Front End | Pending
2024-03-07 | Changes in Set Target Front End | Completed
2024-03-08 | Shivarathri Holiday
2024-03-09 | Implementation of new and existing in Set Target Page | Pending
2024-03-10 | Sunday
2024-03-11 | Implementation of new and existing in Set Target Page | Completed
2024-03-12 | Set Taget back end coding | Pending
2024-03-13 | Set Taget back end coding | Pending
2024-03-14 | Set Taget back end coding | Completed
2024-03-15 | Edit Existing Target Structural design | Pending
2024-03-16 | Edit Existing Target Structural design | Completed
2024-03-17 | Sunday
2024-03-18 | Edit Existing Target Front End Design | Completed
2024-03-19 | Edit Existing Target Back End Codeing | Pending
2024-03-20 | Edit Existing Target Back End Codeing | Completed
2024-03-21 | View Targets | Completed
2024-03-22 | Changes in HTML design | Pending
2024-03-23 | Changes in HTML design | Completed
2024-03-24 | Sunday
2024-03-25 | Holi Holiday
2024-03-26 | Changes in dashboard of admin | Completed
2024-03-27 | Structure planing for user progress update | Pending
2024-03-28 | Structure planing for user progress update | Completed
2024-03-29 | Good Friday Holiday
2024-03-30 | User Completed targets update | Pending
2024-03-31 | Sunday

## April Report
Date | Deatils | Status
2024-04-01 | User Completed targets update | Pending
2024-04-02 | User Completed targets update | Pending
2024-04-03 | User Completed targets update | Completed
2024-04-04 | Research on mail in flask application | Pending
2024-04-05 | Research on mail in flask application | Completed
2024-04-06 | Mail implementation in flask application | Completed
2024-04-07 | Sunday
2024-04-08 | View Target monitration | Completed
2024-04-09 | Ugadi Holiday
2024-04-10 | Excel file import in project | Completed
2024-04-11 | Ramzan Holiday
2024-04-12 | Pdf upload and Download at user end | Pending
2024-04-13 | Pdf upload and Download at user end | Pending
2024-04-14 | Sunday
2024-04-15 | Pdf upload and Download at user end | Completed
2024-04-16 | Modifications in the user viev target page | Pending
2024-04-17 | Modifications in the user viev target page | Completed
2024-04-18 | Seting yearly targets in admin end | Pending
2024-04-19 | Seting yearly targets in admin end | Completed
2024-04-20 | Add Responsibility Mail-Id validation | Pending
2024-04-21 | Sunday
2024-04-22 | Add Responsibility Mail-Id validation | Completed
2024-04-23 | Leave
2024-04-24 | Leave
2024-04-25 | Working on View uploaded file by User | Pending
2024-04-26 | Working on View uploaded file by User | Completed
2024-04-27 | Demo of project completion and Recommended changes
2024-04-28 | Sunday
2024-04-29 | Delete the uploaded PDF file | Pending
2024-04-30 | Delete the uploaded PDF file | Pending

## May Report
Date | Deatils | Status
2024-05-01 | Delete the uploaded PDF file | Pending
2024-05-02 | Delete the uploaded PDF file | Completed
2024-05-03 | Raise Ticket Requirement Analysis | Pending
2024-05-04 | Raise Ticket Requirement Analysis | Completed
2024-05-05 | Sunday
2024-05-06 | Raise Ticket DB Structure design | Pending
2024-05-07 | Raise Ticket DB Structure design | Pending
2024-05-08 | Raise Ticket DB Structure design | Completed
2024-05-09 | Raise Ticket Implementation | Pending
2024-05-10 | Raise Ticket Implementation | Pending
2024-05-11 | Raise Ticket Implementation | Pending
2024-05-12 | Sunday
2024-05-13 | Raise Ticket Implementation | Pending
2024-05-14 | Raise Ticket Implementation | Pending
2024-05-15 | Raise Ticket Implementation | Completed
2024-05-16 | Deaviation Graph Implementation | Pending
2024-05-17 | Deaviation Graph Implementation | Pending
2024-05-18 | Deaviation Graph Implementation | Completed
2024-05-19 | Sunday
2024-05-20 | research on other aspects of development | Pending
2024-05-21 | research on other aspects of development | Completed
2024-05-22 | Leave
2024-05-23 | Leave
2024-05-24 | Verifier login page design | Completed
2024-05-25 | Verifier login validations | Completed
2024-05-26 | Sunday
2024-05-27 | Redesign of index page | Completed
2024-05-28 | Improvements in projects | Completed
2024-05-29 | Improvements in projects | Completed
2024-05-30 | Improvements in projects | Completed
2024-05-31 | Improvements in projects | Completed

## June Report
Date | Deatils | Status
2024-06-01 | Improvements in projects | Completed
2024-06-02 | Sunday
2024-06-03 | Visited office and showed demo | Completed
2024-06-04 | Presentation on project and noted down the chnages | Completed
2024-06-05 | Requirement Analysis | Pending
2024-06-06 | Requirement Analysis | Pending
2024-06-07 | Requirement Analysis | Pending
2024-06-08 | Requirement Analysis | Completed
2024-06-09 | Sunday
2024-06-10 | IQAC Implementation(Index Page) | Completed
2024-06-11 | IQAC Implementation(Dashboard) | Completed
2024-06-12 | IQAC Implementation(Other Features) | Completed
2024-06-13 | IQAC Implementation(Import Attributers) | Completed
2024-06-14 | IQAC Implementation(Alloting Attributes) | Completed
2024-06-15 | IQAC Implementation(Import Employee) | Completed
2024-06-16 | Sunday
2024-06-17
2024-06-18
2024-06-19
2024-06-20
2024-06-21
2024-06-22
2024-06-23 | Sunday
2024-06-24
2024-06-25
2024-06-26
2024-06-27
2024-06-28
2024-06-29
2024-06-30 | Sunday